## Effort and Budget
Càlcul Effort Hours
TCF | Technical Complexity Factor | 1.06
EF | Environmental Factor | 0.95
UUCP | Unadjusted Use Case Points | 65.00
AW | Actor Weighting | 9.00
Càlcul dels Use Case Points
UCP | Use Case Points | 74.17
Càlcul del Estimated Effort
PF | Hours of Effort per Use Case Point | 28
Hours of Effort |  | 2076.66
Càlcul mà d'obra software
Rols |  | Salari anual (€) | Salari anual + SS + altres impostos + import fixe en termes de lloc de treball | Percentatge hores per rol | Hores per rol | Cost de l'hora per rol (€) | Cost total per rol (€)
Cap de projecte |  | 45000 | 63200.00 | 15% | 311.50 | 37.49 | 11676.60
Analista senior |  | 35000 | 49200.00 | 15% | 311.50 | 29.18 | 9090.02
Arquitecte |  | 39000 | 54800.00 | 15% | 311.50 | 32.50 | 10124.65
Analista programador |  | 29000 | 40800.00 | 25% | 519.17 | 24.20 | 12563.44
Programador Júnior |  | 20000 | 28200.00 | 20% | 415.33 | 16.73 | 6946.84
Tester |  | 29000 | 40800.00 | 10% | 207.67 | 24.20 | 5025.37
[6 empty] | Total mà d'obra (€) | 55426.92
Càlcul costos variables
Concepte |  | Quantitat | Cost unitari (€) | Cost (€)
Dispositiu hardware embedded |  | 5000 | 45 | 225000.00
Instal·lació (Tècnic extern) |  | 5000.00 | 10 | 50000.00
0.00
0.00
0.00
0.00
|  |  | Total cost variable (€) | 275000.00
Càlcul cost total
Concepte |  | Cost (€)
Mà d'obra software |  | 55426.92
Despes estructurals - 15% (màrqueting, xarxa, electricitat...) |  | 8314.04
Costos variables |  | 275000.00
Cost (€) |  | 338740.96
Contingències (riscs) - 10% |  | 33874.10
Total Cost (€) |  | 372615.06
Càlcul venda
% marge benefici |  | 15%
benefici |  | 55892.26
Facturació total (€) |  | 428507.31
Preu venta dispositiu (€) |  | 85.70

## Technical
Technical Factor |  | Multiplicador | Magnitud
1 | Distributed System Required | 2 | 5
2 | Response Time Is Important | 1 | 4
3 | End User Efficiency | 1 | 2
4 | Complex Internal Processing Required | 1 | 3
5 | Reusable Code Must Be A Focus | 1 | 3
6 | Installation Ease | 0.5 | 3
7 | Usability | 0.5 | 4
8 | Cross-Platform Support | 2 | 5
9 | Easy To Change | 1 | 2
10 | Highly Concurrent | 1 | 2
11 | Custom Security | 1 | 3
12 | Dependence On Third-Party Code | 1 | 2
13 | User Training | 1 | 1
Calculated TCF |  |  | 1.055

## Environmental
Environmental Factor |  | Multiplicador | Magnitud
1 | Familiarity With The Project | 1.5 | 3
2 | Application Experience | 0.5 | 0
3 | OO Programming Experience | 1 | 4
4 | Lead Analyst Capability | 0.5 | 3
5 | Motivation | 1 | 4
6 | Stable Requirements | 2 | 2
7 | Part Time Staff | -1 | 1
8 | Difficult Programming Language | -1 | 2
Calculated EF |  |  | 0.95

## Use Case
Unadjusted Use Case Points |  | Multiplier | Number of Use Cases
1 | Simple | 5 | 3
2 | Average | 10 | 5
3 | Complex | 15 | 0
Calculated UUCP |  |  | 65
Individual Use Cases |  | Multiplier | Use Case Name
1 | Simple | 5 | Configurar connexió dispositiu
2 | Simple | 5 | Consultar estat del dispositiu
3 | Average | 10 | Gestionar client
4 | Simple | 5 | Gestionar alarmes
5 | Average | 10 | Consultar anàlisi estadístic
6 | Average | 10 | Consultar contracte
7 | Average | 10 | Consultar consum en temps real
8 | Average | 10 | Consultar històric de consum

## Actor
Actor Summary |  | Multiplier | Number of Actors
1 | Simple | 1 | 0
2 | Average | 2 | 0
3 | Complex | 3 | 3
Calculated AW |  |  | 9
Individual Actors |  | Multiplier | Actor Name
1 | Complex | 3 | Tècnic
2 | Complex | 3 | Administratiu
3 | Complex | 3 | Usuari final